## bugs
Bug List
P0 = crash bug, P1 = game stopping but not crash, P2 = not working as expected, P3 = annoying, P4 = nice to have, P5 = future release
# | Reported Date | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce
1 | 2025-02-23 | Ricky | P5 | won't fix (won't be a concern once we separate out the functionality into the level editor mode; player will not exist there) |  | When tile placing, player can "glitch" out of the map if tile is placed on top of the character at the top of the game space, locking player out of map
2 | 2025-02-23 | Ricky | P2 | won't fix (this is not a problem) |  | Sword attack hit box passes through tiles and can deal "damage" through tiles | Attacks should not be able to go through tiles | Attacks can go thorugh tiles | walk up to a 1x1 tile and attack; press attack button, then jump vertically in front of a floating tile such that attack box passes through tile
3 | 2025-02-24 | Ahren | P2 | Resolved | Ahren | When you have a controller (gamepad) connected for a player, the keyboard controls don't work properly | Keyboard controls should either be completely disabled for that player, or work normally (taking a combination of inputs from the gamepad and the keyboard) | The keyboard controls trigger only short pulses of inputs, instead of for example holding the button down | Connect a controller / gamepad. The controls for Player 1 will be messed up.

## bug_severities
Severity | Description
P0 | crash bug; game crashes and is unrecoverable
P1 | game stopping bug, but no crash; cannot keep playing
P2 | serious, game not working as expected
P3 | annoying, could ship but loss of marks
P4 | annoying or limiting, but could be shipped as-is
P5 | minor or feature that nice to have but could ship in future release